## Slide 1
CANREB Steering Committee Review
Project Milestones
Asita Perera
Project Manager
2017-08-31

## Slide 2: Outline
Installation & Commissioning Milestones
Project milestone evolution
Critical path systems
Near critical path systems

## Slide 3: Installation & Commissioning Milestones
Chart: P310 CANREB Milestone Trend Analysis
| 42674 | 42704 | 42735 | 42766 | 42794 | 42825 | 42855 | 42886 | 42916 | 42947 | 42969 | 42978 | 43008 | 43039 | 43069 | 43100 | 43131 | 43159 | 43190 | 43220 | 43251 | 43281 | 43312 | 43343 | 43373 | 43404 | 43434 | 43465
C-283 CANREB HRS System installation complete | 43179 | 43179 | 43179 | 43179 | 43279 | 43279 | 43279 | 43279 | 43339 | 43290
C-746 CANREB RFQ Buncher ready for system testing | 43300 | 43215 | 43298 | 43291 | 43291 | 43291 | 43291 | 43221 | 43221 | 43221
C-1356 CANREB EBIS ready for system commissioning | 43179 | 43179 | 43224 | 43224 | 43242 | 43242 | 43242 | 43326 | 43326 | 43326
C-695 CANREB Nier Spectrometer installation & setup complete | 43244 | 43222 | 43222 | 43222 | 43256 | 43256 | 43167 | 43167 | 43167 | 43167
C-771 P3 & CANREB Commissioning Plan released | 43221 | 43145 | 43217 | 43210 | 43210 | 43210 | 43210 | 43007 | 43007 | 43220
C-775 CANREB HRS commissioned with stable Ion Source | 43482 | 43399 | 43413 | 43406 | 43406 | 43406 | 43406 | 43441 | 43454 | 43425
C-777 CANREB RFQ-EBIS-NIER commissioned with stable Ion Source | 43482 | 43399 | 43413 | 43406 | 43406 | 43406 | 43406 | 43441 | 43454 | 43453
C-779 CANREB RFQ-EBIS-NIER commissioned with ISAC RIB | 43599 | 43523 | 43537 | 43530 | 43530 | 43530 | 43530 | 43564 | 43579 | 43564
D Current Date Line | 42674 | 42704 | 42735 | 42766 | 42794 | 42825 | 42855 | 42886 | 42916 | 42947 | 42969 | 42978 | 43008 | 43039 | 43069 | 43100 | 43131 | 43159 | 43190 | 43220 | 43251 | 43281 | 43312 | 43343 | 43373 | 43404 | 43434 | 43465 | 43496 | 43524 | 43555 | 43585 | 43616 | 43646 | 43677 | 43708 | 43738 | 43769 | 43799 | 43830

## Slide 4: Milestone Evolution 2014-2016
UID | Milestone | Completion in IIA | Feb 2017 SC | Current Rev084 (08/17) | D Feb-Aug (month) | Comment
607 | HRS – Concept design review by an experts committee | 2014-05-01 | 02/2015 | 02/2015 | - | Completed
608 859 860 | HRS – Design review and approval by TRIUMF EBIS – System design review and approval by TRIUMF EBIS – Ordering of superconducting magnets and pumps | Q1.2015 | 09/2015 07/2015 03/2015 | 09/2015 07/2015 03/2015 | - - - | HRS mfg dwgs released. No explicit TRIUMF review in schedule. Completed. Completed Completed
256 1341 | HRS - Start manufacturing EBIS – UHV chambers and vacuum system design done | Q2.2015 | 05/2016 05/2015 | 05/2016 05/2015 | - - | Completed Completed
851 838 | Nier Spectrometer - Design review and approval by TRIUMF RFQ Buncher - Design review and approval by TRIUMF | Q3.2015 | 05/2015 06/2016 | 05/2015 06/2016 | - - | Completed External review completed 06/2016
1639 864 | HRS – Vendor integration and testing completed EBIS - Magnet delivery and off-line test | Q4.2015 | 03/2017 05/2016 | 03/2017 05/2016 | - - | Completed Magnet repaired, completed

## Slide 5: Milestone Evolution 2016-2018
UID | Milestone | Completion in IIA | Feb 2017 SC | Current Rev084 (08/17) | D Feb-Aug (month) | Comment
847 268 1345 743 | Nier Spectrometer - Start manufacturing HRS - System in TRIUMF EBIS - Design of electron gun and electrodes RFQ Buncher - Start components Integration | Q2.2016 | 03/2016 04/2017 08/2015 09/2017 | 03/2016 08/2017 08/2015 09/2017 | - +4 - - | Completed Completed Completed
868 | EBIS - Charge breeding tests at MPIK | Q3.2016 | 04/2017 | 01/2017 | -3 | Completed
283 746 | HRS - Set-up at ARIEL & Ready for System Integration RFQ Buncher Ready for System Integration | Q4.2016 | 03/2018 07/2018 | 07/2018 05/2018 | +4 -2 | Consider shorter optimization time
871 | EBIS - Set-up at ARIEL | Q2.2017 | 01/2018 | 05/2018 | +4 | 
872 695 | EBIS - Injection-Extraction tests Nier Spectrometer - Set-up at ARIEL & Ready for System Integration | Q3.2017 | 04/2018 05/2018 | 07/2018 03/2018 | +3 -2 | Accelerate assembly & installation
1356 | EBIS - Ready for System Integration | Q4.2017 | 05/2018 | 08/2018 | +3 | 
771 | Release Commissioning Plan | Q1.2018 | 04/2018 | 04/2018 | - | 
777 775 | Commissioning of RFQ-EBIS-NIER with stable Ion Source Commissioning of HRS with stable Ion Source | Q2.2018 | 11/2018 11/2018 | 12/2018 11/2018 | +3 - | Could be earlier w/ shorter optimization

## Slide 6: CANREB Project Critical Path: EBIS

## Slide 7: CANREB Diagnostics (ARIEL-II P1 Schedule)
Issue: Unique CANREB Diagnostics assembled later than required (2018-01) for installation on beam line.
Mitigation: Flexibility exists to install them in 2018-03 per current timing.

## Slide 8: Beam Line Installation (ARIEL-II P3 Schedule)

## Slide 9: Near Critical Path
The following CANREB Project systems are near the critical path by the stated schedule float:
RFQ Buncher, ~0.5 months float
HRS Magnets, ~1 month float
HRS Test Ion Source, ~0.5 months float
Nier Magnets, ~5 months float

## Slide 10
Questions?