## Slide 1: Particle Physics Faculty Meeting
Agenda
  Retreat Preparations

## Slide 2
TRIUMF is located on the traditional, ancestral, and unceded territory of thexʷməθkʷəy̓əm (Musqueam) people, who for millennia have passed on their culture, history, and traditions from one generation to the next on this site.
TRIUMF’s home has always been a seat of learning.

## Slide 3
Scenarios
$400M put to government
  Details submitted to government below
  BL1A - triplet exchanged at the end of the 5Y period unless CFI funding awarded
Delay shutdown for a year to finish ARIEL construction and get projects done
  Shutdown in 2026 (Dec 2025-April 2027)
  BL1A - triplet exchanged during the year-long shutdown
Business as usual (as this year) -> ARIEL finished in 2028
  6 months shutdown – 6 months beam (Dec - May shutdown)
  BL1A - triplet exchanged
Transformer replacement in all scenarios
No new NRC positions in either scenario
Things to focus on: What staff and resources needed for each scenario
There appears to be consensus among the divisions that finishing ARIEL is a very high priority.

## Slide 4
Scenarios
400M put to government (“loss of opportunity”)
  The objective in this scenario is to maintain existing science and innovation programs, including medical isotope production for commercial partners, although some impact will be required as staff are re-tasked to other areas. Components delayed are the operations of ARIEL and IAMI, which represents a major loss of opportunity on the international stage, as well as the loss of potential science. Risk is also escalated by deferring the beamline 1A refurbishment by two years, the failure of which would significantly impact materials and quantum science, green technology, and isotope production
Changes from the requested funding level (i.e., $450M) and capabilities are primarily:
  Delay of ARIEL construction for two years, to the end of the five-year period. No operations of ARIEL during the five-year period, just commissioning. This defers the operation of ARIEL beyond the CERN long shutdown, missing an opportunity for Canada to provide global leadership in ISOL based discovery while a primary competing facility, ISOLDE at CERN, is shutdown.
  Deferral of IAMI operations for two years. Such a delay will impact the ability of IAMI to develop new life saving drugs and risks the reliability of production of medical isotopes. This will also impact potential future commercial revenue as it will naturally defer clinical trials of new drugs.
  Deferral of beamline 1A refurbishment by two years, halving the cost in this plan by extending the cost into the next funding cycle. This significantly increases the risk to the material science, quantum, and irradiation science programs should a major failure occur. It also increases the risk of production of actinium and commensurate potential impact on reputation and commercial revenues.
  Reduction in request by 57 staff to 444 staff average to just below the contemporary staffing plan. This reduction is a combination of reduced staff due to deferred implementation of the major infrastructure projects and a reorganisation to support operational excellence, with a commensurate loss of capability for the broader research ecosystem in science and engineering. This impacts our ability to fully support domestic and international projects with commensurate loss of impact and reputation.
  MRO costs remain the same, assuming all legacy and existing systems are operated at the same level of science capacity.
  Commercial revenue is assumed to be similar to the full request, contributing $20M to operational support over the 5-year period.