## Slide 1: ARIEL Completion Timeline, Sequencing, 5Y Scenarios PSD BAE Retreat
May 23, 2024
Alexander Gottberg
ARIEL Program Leader
Targets and Ion Sources Department Head Research Scientist

## Slide 2
With ISAC and ARIEL, TRIUMF hosts the highest-power ISOL facilities in the world.

## Slide 3
Tripling TRIUMF‘s Radioisotope Science Program
Advanced Radioisotope Laboratory (ARIEL)
ARIEL-I (2012 - 2014) e-linac, beam tunnel, target building
ARIEL-II (2017 - 2028) target stations, shielding, hot cells, RIB distribution
CANREB (2014 - 2019) charge state breeding and purification for post-acceleration in ISAC II
Therapeutic Isotopes (2020 - 2028) production and processing of medical isotopes at ARIEL proton target station
$200 million investment by federal and 6 provincial governments; supported by 21 universities across Canada, about 700 FTE years total effort.

## Slide 4
ARIEL will triple TRIUMF’s radioisotope beam science

## Slide 5: An Independent Driver for TRIUMF’s Rare Isotope Program
500 MeV x 10 µA protons [1/s]
in-target production intensity from UCx
30 MeV x 10 mA electrons [1/s]
→ BL4N (protons from main cyclotron)
→ e-linac (30 MeV electrons) plan: ≤3 mA, 100 kW! (limited by target)

## Slide 6: ARIEL Scope
ARIEL Ultimate Objectives:
Two new radioisotope production target stations 50 kW protons and 100 kW electrons
Multi-user operation up to three simultaneous isotope beams (9000 RIB hours) delivered to the existing experimental facilities
More efficient post acceleration electron beam ion source - charge state breeder, radiofrequency quadrupole, Nier-spectrometer and unique 1/20,000 resolution high-resolution mass separator.
Medical Isotopes production in proton target station beam dump and transfer to medical isotope research

## Slide 7: ARIEL Program Timeline
2012
783 days
Jan 1 - Dec 31
1523 days
Jan 1 - Nov 1
2522 days
Aug 1 - Apr 1
1216 days
May 1 - Dec 27
300 days
Jan 1 - Feb 24
175 days
Feb 1 - Oct 2
133 days
Jun 30 - Dec 31
1130 days
Jan 1 - May 1
75 days
Nov 1 - Feb 13
2029
ARIEL-I
CANREB
ARIEL-II: Proton & Electron Stations
Therapeutic Isotopes
Today
2012
2014
2016
2018
2020
2022
2024
2026
Target Building construction, beam tunnel, e-linac
charge state breeding and purification for post-acceleration in ISAC II
Concept & Design
Shielding Component Installation
Target Station Installation
AETE Integration & Commissioning
APTW Integration & Commissioning
Beam Line Installations
Integration
& Commissioning
2028

## Slide 8
The ARIEL facility is taking shape!

## Slide 9: Status of ARIEL
Nominal driver beam parameters achieved, commissioning in progress.
Target ion source system fully prototyped, tested without beam and in fabrication
Target hall shielding 92% design completed, 70% installation completed
Hot cell (largest single capital invest) installation completed
200 m of RIB distribution line installed and commissioned
HRS 1/13,0000 mass resolution achieved
Radioactive isotopes from ISAC injected into CANREB, charge-state boosted and post-accelerated in ISAC II, issues with EBIS being addressed.
Nominal electron beam
BL4N vault installation
Target shielding installation
RIB transport system
ARIEL hot cell
Target system prototype
ARIEL HRS
Target module design completion

## Slide 10
RIB Program Integration into 5YP Scenarios

## Slide 11: Preparation of three 5YP scenarios
The scenarios the TRIUMF Leadership Team identified were (Leadership retreat Monday May 13th):
The scenario articulated to the government
  ARIEL construction is slowed and operations of ARIEL and IAMI are delayed, resulting in the loss of first-mover advantage against international competition from ISOLDE
  Increased risk of infrastructure failure due to reduced investment in deferred maintenance
  Decreased science output with internal resources and staff reorganised to fill operational requirements
  Delayed BL1A refurb except CFI project will be granted
Line-up for a one year shut down in 2026 (ARIEL, BL1A, site infrastructure, management systems)
  Will require a detailed planning to line-up design and procurement for the 2026 installation phase
  Use the shut down for BL1A triplet replacement
  Completion of ARIEL CFI project in 2027, investments for initial ramp up
  Start TR24 operation already in early 2025 and get financial support from BWXT to run earlier.
Scenario with 6 months of operation additional projects and project progress only as additional funding allows
  Completion of ARIEL core project in 2028
  Little to no ARIEL operation
  Further deferral of scope items already deferred from CFI ARIEL-II program
  BL1A if CFI project is successful

## Slide 12: Shutdown (Scenario 2) and Beam Operation Considerations – Lab Wide
ARIEL is the flagship project and could get a significant boost from a focus period in the lab. However, is is not the only aspect driving the decision. Other projects considered to be moved forward in this time include:
  Weft and Warp, management systems, regulatory compliance
  BL1A
  ISAC refurbishment
  Deferred maintenance
  Substation refurbishment
Impact on non-isotope beam science programs need to be considered (µSR, DarkLight, THz, UCN, radiation therapy research,…)
Financial impact: revenue vs savings, including potential damage in costumer relations
Loss of knowledge critical for operations
HQP engagement, student projects
NSERC project timelines – Nigel mentions that NSERC will be informed and accommodations by NSERC should be expected.

## Slide 13: Current ARIEL Programme Critical Path
July
2028
January
2028
July
2027
January
2027
July
2026
January
2026
July
2025
January
2025
July
2024
January
2024
APTW Module Manufacture, Assembly, Offline Testing
APTW Module Installation & Integration
APTW Commis- sioning
AETE Module Manufacture, Assembly, Offline Testing
AETE Module Installation & Integration
AETE Commis-sioning
Shielding Component Installation
Services Install
Shielding
Current AETE
Current APTW
AETE first beam
APTW first beam
Electron target station installation completing late 2026, proton target station installation completing late 2027
Electron beam target commissioning starting in 2027, proton beam target commissioning starting in 2028
First beam to an experiment is currently planned for 2029.
Scope deferred from CFI project prohibitive for meaningful ARIEL RIB user program in 2025-30 in Scenarios 1 and 2.

## Slide 14: Programme Acceleration Opportunity in Scenario 2
Proposal:
Use of (additional) time for target pit shielding for offline assembly of modules, target pit services room installation
Complete proton and electron beamlines installation during shielding installation 2025
TRIUMF makes significant additional technical (+29 FTE) resources available throughout CY 2026.
Benefit:
Parallelization of AETE and APTW installation (currently sequential in the schedule) allowing for completion in 2026.
Beam on both stations in 2027,
Increase RIB reach by swapping APTW/AETE commissioning sequence, accelerating spallation and medical isotopes
Front-load CANREB, ramp-up relevant ARIEL deferred scope (target production laboratories, spent target storage vault)
Leading to an effective acceleration of CFI project completion of 1-2 years and ARIEL ramp up by up to 4 years.
RIB benefit outside ARIEL: ISAC-ARIEL operational integration, getting ISAC to accommodate 8 months of beam operation

## Slide 15: Programme Acceleration Opportunity
July
2028
January
2028
July
2027
January
2027
July
2026
January
2026
July
2025
January
2025
July
2024
January
2024
APTW Module Manufacture, Assembly, Offline Testing
APTW Module Installation & Integration
APTW Commis- sioning
AETE Module Manufacture, Assembly, Offline Testing
AETE Module Installation & Integration
AETE Commis-sioning
Shielding Construction
Services Install
AETE and APTW Module Manufacture, Assembly, Offline Testing
AETE and APTW Module Installation & Integration
AETE and APTW Commissioning
Shielding
Current AETE
Current APTW
Accelerated
AETE first beam
APTW first beam
AETE and APTW first beam

## Slide 16: Resource Requirements
The sequencing of AETE and APTW installation is a result of resource leveling, not technical limitation
To execute the accelerated option, a total of 36 FTE years need to be pulled forward and put in parallel with existing ARIEL resources.
Required additional resource profile:
  4/36 additional FTE years in 2025 to support the preparation of the focussed installation
  29/36 additional FTE years in 2026.
  3/36 additional FTE years in 2027 to support parallel commissioning activities.
About 87 FTE reported for online operation – head count seems ok
Major critical contributions to additional required FTE in 2026 identified and critical group leaders being consulted to match
Skill | Additional required in 2026 | Potentially identified from critical groups
Technical.Mechanical | 6 | 8
Engineering.Mechanical | 4 | 7
Physics.Accelerator | 7 | 7
Engineering.Control | 3 | 5
Engineering.Electrical | 2 | 2
Technical.Electrical | 2 | 2
Technical.Mechanical Design | 1 | 

## Slide 17: Additional Requirements
To fully leverage the early completion and move into ramp-up, additional work is required:
Realizing some of the previously deferred scope:
  E-linac upgrades
  ARIEL spent target storage vault
  Target conditioning station completion
  RIB target laboratories
  HV target infrastructure upgrade
  CANREB systems upgrade
Front-loading ISAC target system refurbishment
Front-loading TRILIS upgrades
Front-loading of licensing activities
The above activities (except licensing) have been budgeted and capacity matched in Accelerator Division Initiatives Priority 1 list for 2025-30.

## Slide 18
Radioisotope Beam Projections

## Slide 19: Baseline – ISAC Continues in Current Mode of Operation
Chart: RIB Hours in Different Scenarios
| 6 month operation | 6 month operation | 6 month operation | 6 month operation |  |  | 6 month operation |  |  | 6 month operation |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
ITE/ITW | 3200 | 3200 | 3200 | 3200 | 3200 | 3200
APTW | 0 | 0 | 0
AETE | 0 | 0 | 0
total RIB hours | 3200 | 3200 | 3200 | 3200 | 3200 | 3200
accumulative, 6 month operation | 3200 | 3200 | 3200 | 3840 | 4480 | 5120 | 5760 | 6400 | 7040 | 7680 | 8320 | 8960 | 9600 | 10240 | 10880 | 11520 | 12160 | 12800 | 13440 | 14080 | 14720 | 15360 | 16000 | 16640 | 17280 | 17920 | 18560 | 19200
Comments:
Scenario 1 – as articulated to government
  ARIEL completion slows down
  No ARIEL operation within 5YP
ISAC continues to operate from June to December, generating about 3200 RIB hours per year available to experiments
Impact:
Shutdown overhead same as when operating full 8 months.
Resource competition with ISAC refurbishment and ARIEL completion throughout all of 5Y

## Slide 20: Scenario 2 – 2026 Shutdown – Comparison with ISAC Generated RIB alone
Chart: RIB Hours in Different Scenarios
| 6 month operation | 2026 SD, ISAC only |  | 6 month operation | 2026 SD, ISAC only |  | 6 month operation | 2026 SD, ISAC only |  | 6 month operation | 2026 SD, ISAC only |  | 6 month operation | 2026 SD, ISAC only |  | 6 month operation | 2026 SD, ISAC only |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
ITE/ITW | 3200 | 3200 | 3200 | 0 | 0 | 3200 | 4400 | 3200 | 4400 | 3200 | 4400 | 3200 | 4400
APTW | 0 | 0 | 0 | 0 | 0 | 0 | 0
AETE | 0 | 0 | 0 | 0 | 0 | 0 | 0
total RIB hours | 3200 | 3200 | 3200 | 0 | 0 | 3200 | 4400 | 3200 | 4400 | 3200 | 4400 | 3200 | 4400
accumulative, 6 month operation | 3200 | 3200 | 3200 | 3840 | 4480 | 5120 | 5760 | 6400 | 7040 | 7680 | 8320 | 8960 | 9600 | 10240 | 10880 | 11520 | 12160 | 12800 | 13440 | 14080 | 14720 | 15360 | 16000 | 16640 | 17280 | 17920 | 18560 | 19200
Chart: RIB Hours in Different Scenarios
| 6 month operation | 2026 SD, ISAC only |  | 6 month operation | 2026 SD, ISAC only |  | 6 month operation | 2026 SD, ISAC only |  | 6 month operation | 2026 SD, ISAC only |  | 6 month operation | 2026 SD, ISAC only |  | 6 month operation | 2026 SD, ISAC only |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
ITE/ITW | 3200 | 3200 | 3200 | 0 | 0 | 3200 | 4400 | 3200 | 4400 | 3200 | 4400 | 3200 | 4400
APTW | 0 | 0 | 0 | 0 | 0 | 0 | 0
AETE | 0 | 0 | 0 | 0 | 0 | 0 | 0
total RIB hours | 3200 | 3200 | 3200 | 0 | 0 | 3200 | 4400 | 3200 | 4400 | 3200 | 4400 | 3200 | 4400
accumulative, 6 month operation | 3200 | 3200 | 3200 | 3840 | 4480 | 5120 | 5760 | 6400 | 7040 | 7680 | 8320 | 8960 | 9600 | 10240 | 10880 | 11520 | 12160 | 12800 | 13440 | 14080 | 14720 | 15360 | 16000 | 16640 | 17280 | 17920 | 18560 | 19200
accumulative, ISAC only | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 4080 | 4960 | 5840 | 6720 | 7600 | 8480 | 9360 | 10240 | 11120 | 12000 | 12880 | 13760 | 14640 | 15520 | 16400 | 17280 | 18160 | 19040 | 19920 | 20800
Comments:
Scenario 2 – 2026 shutdown and ARIEL project acceleration.
ISAC moves back to 8 months operation, generating about 4400 RIB hours per year available to experiments
Impact:
Shutdown overhead fraction reduced.
Resource competition with ARIEL greatly reduced
Break-even point in accumulated RIB hours reached 2028-2029

## Slide 21: Scenario 2 – 2026 Shutdown – Factoring in Additional RIB Hours from ARIEL
Chart: RIB Hours in Different Scenarios
| 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
ITE/ITW | 3200 | 3200 | 3200 | 3200 | 0 | 0 | 3200 | 4400 | 4400 | 3200 | 4400 | 4400 | 3200 | 4400 | 4400 | 3200 | 4400 | 4400
APTW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 660 | 660 | 990
AETE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 660 | 660
total RIB hours | 3200 | 3200 | 3200 | 3200 | 0 | 0 | 3200 | 4400 | 4730 | 3200 | 4400 | 5390 | 3200 | 4400 | 5720 | 3200 | 4400 | 6050
accumulative, 6 month operation | 3200 | 3200 | 3200 | 3840 | 4480 | 5120 | 5760 | 6400 | 7040 | 7680 | 8320 | 8960 | 9600 | 10240 | 10880 | 11520 | 12160 | 12800 | 13440 | 14080 | 14720 | 15360 | 16000 | 16640 | 17280 | 17920 | 18560 | 19200
accumulative, ISAC only | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 4080 | 4960 | 5840 | 6720 | 7600 | 8480 | 9360 | 10240 | 11120 | 12000 | 12880 | 13760 | 14640 | 15520 | 16400 | 17280 | 18160 | 19040 | 19920 | 20800
Chart: RIB Hours in Different Scenarios
| 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 6 month operation | 2026 SD, ISAC only | 2026 SD, incl ARIEL | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
ITE/ITW | 3200 | 3200 | 3200 | 3200 | 0 | 0 | 3200 | 4400 | 4400 | 3200 | 4400 | 4400 | 3200 | 4400 | 4400 | 3200 | 4400 | 4400
APTW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 660 | 660 | 990
AETE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 660 | 660
total RIB hours | 3200 | 3200 | 3200 | 3200 | 0 | 0 | 3200 | 4400 | 4730 | 3200 | 4400 | 5390 | 3200 | 4400 | 5720 | 3200 | 4400 | 6050
accumulative, 6 month operation | 3200 | 3200 | 3200 | 3840 | 4480 | 5120 | 5760 | 6400 | 7040 | 7680 | 8320 | 8960 | 9600 | 10240 | 10880 | 11520 | 12160 | 12800 | 13440 | 14080 | 14720 | 15360 | 16000 | 16640 | 17280 | 17920 | 18560 | 19200
accumulative, incl. ARIEL | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 4146 | 5092 | 6038 | 6984 | 7930 | 9008 | 10086 | 11164 | 12242 | 13320 | 14464 | 15608 | 16752 | 17896 | 19040 | 20250 | 21460 | 22670 | 23880 | 25090
accumulative, ISAC only | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 4080 | 4960 | 5840 | 6720 | 7600 | 8480 | 9360 | 10240 | 11120 | 12000 | 12880 | 13760 | 14640 | 15520 | 16400 | 17280 | 18160 | 19040 | 19920 | 20800
Comments:
Scenario 2 – 2026 shutdown and ARIEL project acceleration.
ISAC moves back to 8 months operation, generating about 4400 RIB hours per year available to experiments.
ARIEL gradually ramping up to 2-3 targets per year per station in 2030
Impact:
Shutdown overhead fraction reduced
Resource competition with ARIEL greatly reduced and site-wide services less loaded from ARIEL
Break-even point in accumulated RIB hours reached earlier.

## Slide 22
Electrons versus Protons

## Slide 23: Projecting ARIEL AETE Yields
FLUKA ISAC in-target isotope production rates from UCx [1/s]
FLUKA AETE in-target isotope production rates from UCx [1/s]
10 kW electron beam power
10 kW proton beam power

## Slide 24: Projecting ARIEL AETE Yields
FLUKA ISAC in-target isotope production rates from UCx [1/s]
FLUKA AETE in-target isotope production rates from UCx [1/s]
scaled to 10 kW electron beam power
scaled to 10 kW proton beam power
Isotope production ratio AETE vs ISAC per kW

## Slide 25: ARIEL AETE and APTW Projected Yields
Projected LE Isotope Rates from APTW [1/s]
Initial ARIEL APTW yields will be comparable to current average ISAC yields
And: capabilities for new target materials, target ion source concepts, molecular beam formation, etc
Projected LE Isotope Rates from AETE [1/s]
Initial ARIEL AETE yields projected using measured ISAC-UCx isotope extraction efficiencies
Differences in geometry and material microstructure will require confirmation and additional R&D
10 kW electron beam power
The parallelization of APTW and AETE installation would allow to swap APTW and AETE commissioning making spallation beams and medical isotopes available sooner.

## Slide 26: Next Steps
Continue conversation on different scenarios.
If lab commits to a 2026 shutdown to complete ARIEL in 2027 and start RIB ramp up 2025-30:
Planning, planning, planning
  Review of activities
    Parallelization of target systems installations and integration
    Beamline installations
    Realization of previously deferred scope that is required for ramp up
    ISAC systems refurbishments and upgrades
    Additional fabrication and procurement tasks
    Required licensing activities towards commissioning and operation
  Allocate budgets at finalization of NRC contribution agreement (Fall 2024)
  Complete resource-loaded schedule of all related activities (late CY 2024)
  All resources committed and negotiated with relevant group leaders (late FY24/25)

## Slide 27
Discovery,
accelerated
Thank you Merci
Follow us @TRIUMFLab
www.triumf.ca

## Slide 28: ARIEL Targetry Systems
module storage
spent target storage
protons
electrons
AETE
APTW
drivers beam tunnel
RIB
RIB
ASTM
Hot cell facilities
Remote-controlled crane
2000 t of steel and concrete components
Modular RH high-power infrastructure
Symbiotic medical target in APTW beam dump

## Slide 29: RIBs Availability from all ISAC Targets Over the Years
[1/s]

## Slide 30: Origin of the Areas of Poor Isotope Release
Experimental LE Isotope Rates at ISAC since 2000 [1/s]

## Slide 31: ISAC Isotope Extraction Efficiency
Average experimental ISAC LE isotope rates from UCx [1/s]
FLUKA ISAC in-target isotope production rates from UCx [1/s]
scaled to 10 kW proton beam power
10 kW proton beam power

## Slide 32: ISAC Isotope Extraction Efficiency
Average experimental ISAC LE isotope rates from UCx [1/s]
FLUKA ISAC in-target isotope production rates from UCx [1/s]
scaled to 10 kW proton beam power
scaled to 10 kW proton beam power
Average isotope extraction efficiencies from ISAC UCx

## Slide 33: Electron-Driven ISOL Challenges
e-
Target
Converter
γ
Ion source
e- 30 MeV, 100 kW
Separator
magnet
A
++
++
A
A
++
A
++
A
++
A
++
A
++
A
++
A
++
++++
A
A
++
++
A
A
++
e- LINAC
γ
60 kV Target and ion source
2000 oC
Radioactive ion beams
→ Thin target or change of orientation
→ ISAC target geometry not viable for AETE.
→ ISAC isotope extraction efficiencies not directly applicable to ARIEL AETE, but best assumption available…

## Slide 34: ARIEL Program Organisation Chart

## Slide 35: ARIEL CFI Projects Objectives
Hot Cell
  A hot cell facility supporting ARIEL MRO
  90% completed – Hot cell installation completed. Temporary east shielding and minor technical modifications required.
CANREB beam lines
  Beamline switchyard, delivering RIB from both ARIEL target stations into ISAC and CANREB.
  Beamline installation 98% complete, CFI milestone delivered (2019), receiving operational funds (IOF)
High-Mass Rare Isotope Beam from ISAC to ARIEL to ISAC
  Beamline switchyard, delivering RIB from ISAC into CANREB-EBIS and back into ISAC post accelerator.
  Demonstrated and CFI milestone delivered (2020)
ARIEL Electron Target East (AETE)
  A design for a capable and innovative electron-driven ISOL target station with clear upgrade path towards 100 kW operation.
  Target module design completed; CFI design milestone delivered.

## Slide 36: ARIEL CFI Projects Objectives
Ions from AETE to ISAC
  AETE installed and capable of delivering a heavy ion beam into the ISAC experimental facility.
Photo-fission Rare Isotope Beam to yield station
  Low-power (<1 kW) electrons delivered to an AETE actinide target and RIB extracted, transported and detected at ARIEL yield station.
Rare Isotope Beams from ARIEL Proton Target West to yield station (ARIEL-II Project Complete)
  Low-power (<1 kW) protons delivered to an APTW target and RIB extracted, transported and detected at ARIEL yield station.
Therapeutic Isotopes Produced in secondary APTW target and delivered to medical isotope research facility (Rare Isotopes for Cancer Therapy Project Complete)
  Irradiate a secondary target in APTW, co-producing medically relevant radioisotopes
  Transport of irradiated secondary target to a medical isotope research facility (via the ARIEL hot cell facility).
Priority is to conclude CFI projects, meaning to work on 5-8 and day-1 deliverables.

## Slide 37: Hub for Training and R&D
High-power ISOL targets
ARIEL is a platform for student projects across all disciplines (engineering, math, physics, graphics design, chemistry) and all levels (high school students, 30+ coop students, 8+ master students, 10+ PhD students, post-docs)
Example: The joint University of Victoria /TRIUMF accelerator research program
2 joint faculty positions,
NSERC grant for student support in accelerator physics since 2011
  6 PhD, 4 MSc (6 international)
  So far 1 PhD and 4 MSc theses finished
One lecture taught by the adjunct faculty each year
Research topics:
  Beam physics and instrumentation (R. Baartman, T. Planche, O. Kester)​
  Superconducting RF (R. Laxdal, T. Junginger)​
  Ion Sources and Targets (A. Gottberg, O. Kester) ​
Dust in Accelerators
Target Materials
RIB Ion Sources
Material Radiation Damage
More efficient SRF Cavities