## Slide 1: Status of FAIR
Yvonne Leifels
GSI Helmholtzzentrum für Schwerionenforschung, Darmstadt /
FAIR Facility for Antiproton and Ion Research

## Slide 2
CBM
NUSTAR HEB
S-FRS
SIS100
CRYO 2
April 2024, D. Fehrenz, GSI FAIR
Outline
Introduction
Civil construction
  Concrete works completed
  Cables, ventilation, etc (TBI) ongoing
Accelerators
  Installations started beginning of 2024
Experiments
  On track for FAIR 2028
FAIR Commissioning
  Start in 2025
  First experiments with Super-FRS@SIS18 end of 2027/2028

## Slide 3
New management team

## Slide 4
FAIR Facility for Antiproton and Ion Research
GSI Helmholtzzentrum
für Schwerionenforschung
Notes: ESFRI Landmark and strategic goal of the nuclear physics community, 3000 users from more than 50 countries

## Slide 6: GSI and FAIR – Facilities
SIS !00
Super FRS
SIS18
UNILAC
100 m
HESR
CR
ESR
CRYRING
FRS
HITRAP
ESR, CRYRING, & HITRAP are part of FAIR
GSI, existing (upgraded to integrate with FAIR)
Synchrotron SIS100
Super-FRS
Storage rings
Antiproton beams

## Slide 7: FAIR Status
NUSTAR LEB
S-FRS
NUSTAR HEB
CBM
CRYO2
SIS100
APPA

## Slide 8: FAIR Progress – Civil Construction
View of south area with all buildings completed and soil modelling in progress

## Slide 9: FAIR Progress – Civil Construction
View of north area (SIS100) with all buildings completed

## Slide 10: FAIR Project – Civil Construction
Central transfer building

## Slide 11
FAIR Project - Current Scope

## Slide 12: FAIR Progress – Accelerators SIS100

## Slide 13: FAIR Progress - Accelerators Super-Fragment Separator
Experimental sites
Target area
Low energy branch
High energy
branch
CR
Target flask installed
Lateral shielding installed
Installation 1st multiplett

## Slide 14: FAIR Progress - FAIR Control Center
Main control room for FAIR & GSI accelerators with new FAIR Control System
Completion mid 2026
Main Control Room
Conference rooms
Offices

## Slide 15: FAIR Progress – Experiments CBM Cave
Experiment platform and magnet foundation
ready for next installation steps
Artistic view of CBM and HADES experiment
Notes: CBM and HADES cave

## Slide 16: FAIR Progress - Experiments
CBM Silicon Tracker
Silicon Tracker
DESPEC
Gamma-ray
hybrid array
Barrel DIRC
Diamond anvil cells
R3B Proton Arm Spectrometer
Schottky
detectors
Laser
technology
3d printed modulator
Cryogenic
stopping
cell

## Slide 17: FAIR Phase-0 Stepwise approach to FAIR science
FAIR Phase-0 started in 2019
100 days of beam time per year until FAIR starts operation
Commissioning and operation of upgraded GSI accelerators and newly built FAIR detectors

## Slide 18: FAIR Progress – Commissioning Start in 2025
Q3 2025: Start of commissioning of Cryo plant and Cooling water system
Q4 2025: Initial steps for HEBT commissioning
Q4 2025: Takeover of main control room in FAIR Control Center (FCC)

## Slide 19: Integrated Time Schedule
2024 2025 2026 2027 2028
Beam Time
Beam Time
Beam Time
GSI ACC operation with new FAIR control system
from new FAIR Control Center
FAIR Control Center and Technical infrastructure - Construction
Beam Commissioning
FAIR Hardware-Commissioning Super FRS
Cryo 2 Commissioning
FAIR Hardware-Commissioning SIS-100
Beam Commissioning
Beam Time
FAIR Accelerator / Experiments - Procurement, Manufacturing & Installation
start of early
science program
start of first
science program
& first science+ program
FAIR Buildings and Technical Infrastructure - Construction

## Slide 20
Thank you!
Questions?

## Slide 21
Sweden
France
India
Finland
Germany
Poland
Romania
Russia
Slovenia
UK
FAIR’s international convention
  9 shareholders:
  + 1 associated partner:
  + 1 aspirant partner:
3000 users from more than 200 institutions from 53 countries are involved
Notes: Germany, Slowenia, Romania, Poland, Russia, India, Finland, Sweden, UK, Czech

## Slide 22: FAIR Phase-0 Scientific Programme
HITRAP
DESPEC

## Slide 23: FAIR Phase-0 Highlights Bound state β-decay of 205Tl81+
205Tl is a stable atom, the bare 205Tl81+ nucleus decays to 205Pb
Process becomes relevant in stellar medium (~10 Millionen Kelvin)
Modifies the abundance of 205Pb
  which is created by slow in neutron capture in AGB stars
205Pb abundance relevant for the evolution of the solar system
Half-life of
205Tl81+ ~290Tage
G. Leckenby et al., Nature (2024)
R. S. Sidhu et al., Phys. Rev. Lett. (2024)

## Slide 24: Vision for the future: FAIR 2028
FAIR in 2028 will feature the most valuable science program which can be hosted in the then existing infrastructure
The „FAIR 2028“ science program will include:
  APPA experiments at the low-energy rings, at SIS100, at the caves at SIS18 and UNILAC with and at PHELIX and a limited set of experiments which could be hosted at all the caves served by SIS100
  NUSTAR at the Super FRS with SIS100 beams, plus SHE experiments at UNILAC and ILIMA at the low-energy rings
  CBM at the new cave with SIS100 beams, and HADES at SIS18
  PANDA is developing a hadron physics program to be carried as bridge towards the program with antiprotons, when possible using the caves and beams available at GSI/FAIR and synergies with other experiments