## Slide 1: ARIEL Discussion Particle Physics Meeting
May 8, 2025
Alexander Gottberg
ARIEL Program Leader Senior Scientist Department Head – Targets and Ion Sources

## Slide 2: ARIEL Scope and Status

## Slide 3: ARIEL Technical Deliverables
Driver beams
30 MeV, 100 kW electron linac
BL4N 500 MeV extraction probe from main cyclotron
Shared driver beam transport tunnel
Electron beamline to AETE
Proton beamline (cyclotron to APTW)
Proton and electron beam entrance modules
Two new radioisotope production target stations
AETE 100 kW electron target and APTW 50 kW protons,
Target auxiliary systems, mechanical and electrical services
Shielding, remote handling, target production laboratories, waste management
Beam dump module…

## Slide 4: ARIEL Technical Deliverables
RIB Beam transport
RIB extraction modules
RIB switchyard (ARIEL target stations to ISAC and CANREB)
CANREB (HRS, EBIS, RFQ) and ARIEL yield station
Medical Isotopes
Medical target irradiation module,
Medical target transfer system,
Target send/receive station and packaging infrastructure
Integration
Mechanical, electrical, ventilation, safety systems,
Control system
Safety and regulatory documentation

## Slide 5: Status of Electron and Proton Driver Beams
Completed:
High-intensity 30 MeV electron linac
Produced nominal electron beam at the e-linac and delivered beam to high-energy beam dump for several days at a time
500 MeV BL4N extraction probe in the cyclotron
Construction of driver-beam transport tunnel
Ongoing:
Electron and proton beam lines
Integration and testing of the joint machine protection system
Commissioning electron linac, proton beam extraction and initial transport to AETE and APTW
Electron and proton target stations beam entrance modules
Nominal electron beam

## Slide 6: Status of Target Systems
Completed:
Target building and building systems
Target ion source systems designed and prototyped
Target shielding and embedded services, last fixed shielding installation ongoing
Hot cells and module storage structure
ARIEL laser ion source installation
Ongoing:
Target production laboratories
High-active water, gas supply, radioactive gas decay systems, target pit services room installation
Target station modules assembly and installation
Medical target transfer/send/receive station installation
Removable and entrance shielding
Target decay storage vault

## Slide 7: Status of Beam Delivery Systems
Completed:
250 m of RIB beam distribution switchyard
CANREB HRS with world-record mass resolving power
ARIEL yield station
Ongoing:
Address remaining issues with CANREB EBIS and CANREB RFQ
HRS HV enclosure
Target station RIB modules

## Slide 8: ARIEL Organization
A

## Slide 9
Tripling TRIUMF ‘s Radioisotope Science Program
Advanced Radioisotope Laboratory (ARIEL)
ARIEL-I (2012 - 2014) e-linac, beam tunnel, target building
ARIEL-II (2017 - 2027) target stations, shielding, hot cells, RIB distribution
CANREB (2014 - 2019) charge state breeding and purification for post-acceleration in ISAC II
Therapeutic Isotopes (2020 - 2027) production and processing of medical isotopes at ARIEL proton target station
$200 million investment by federal and 6 provincial governments; supported by 21 universities across Canada, about 700 FTE years total effort.
A

## Slide 10: ARIEL Organization Chart
C

## Slide 11: Planning towards LS26
LS26
2012
783 days
Jan 1 - Dec 31
1523 days
Jan 1 - Nov 1
2522 days
Aug 1 - Apr 1
1216 days
May 1 - Dec 27
300 days
Jan 1 - Feb 24
175 days
Feb 1 - Oct 2
133 days
Jun 30 - Dec 31
1130 days
Jan 1 - May 1
75 days
Nov 1 - Feb 13
2029
ARIEL-II: Proton & Electron Stations
Therapeutic Isotopes
Today
Driver Beam Lines
ARIEL Operations Ramp Up
E-linac Upgrades
First Beam on AETE
First Beam on APTW
Med. Isotopes to Users
Three Beam Capability
Med. Isotopes CFI Early Closeout
ARIEL User Operation
Q1
Q2
Q3
Q4
CY 2024
Q1
Q2
Q3
Q4
CY 2025
Q1
Q2
Q3
Q4
CY 2026
Q1
Q2
Q3
Q4
CY 2027
Q1
Q2
Q3
Q4
CY 2028
ARIEL-II CFI Early Closeout
Fixed Component Installation
FE Assem, Tests
Target Modules
Offline Installation
Construction
RIB & Entrance Modules
Assem, Testing
Manuf.
Beam Dumps
Assem.
Integr, Design, Manuf.
Installation, Integration
Removable shielding Install
Install
Install
Install
Alignment Rails
Det. Design
Manuf.
Installation
Secondary Gas*
Offline Manufacturing
Install
Service Spaces
Installation
High-Voltage Chases*
Auxiliary Systems*
Installation
Offline Prep
Installation
Offline Prep
Manufacturing
Assem, Testing
Testing, Commissioning
Commissioning
Commissioning
Commissioning
Test., Comm.
Shielding
Medical Target*
Transfer System
Installation
Installation
Design, Prototype
Manufacturing
Commissioning
Manufacturing
Commissioning
Installation
Spent Target Vault
Target Laboratories*
CANREB Upgrades
Installation
Power & Reliability Ramp-Up
Production Ramp Up
Installation
Det. Design
Manuf.
Conv. Chem.
Actinide Chemistry
Assembly Lab
ARIEL Core Team
Start FTE ramp-up
Expanded Team
Transferring resources to ops and other projects
C

## Slide 12: Project Goals for 2025 to 2027
2025 is the foundation for 2026
Complete most of the designs, while keeping the machine shop fully occupied in 2025 and into 2026
First equipment needs to be ready to install in TH in October
In 2026, people will be ready and available to help
Planning is essential: Machine shop finishes items as they are needed
In 2026 we need to use the available resources to advance the assembly and installation
By the end of 2026, we are aiming at installation completed but not perfected for all the above systems
Commissioning in 2027 and start of beam delivery in 2028
C

## Slide 13: Requests for Contributions
A

## Slide 14: Expanding the ARIEL Team
Several groups previously outside the core ARIEL team have taken ownership of large work packages. Examples:
SciTech – Target stations mechanical services (secondary gas management, high-active gas storage,…)
SRF - Target hall entrance shielding, Target Pit Services Room entrance shielding, target actuators
TPO – High-voltage chases, high-voltage connections, high-voltage terminals, target production labs
Ops – Overall cable management, installation team support
ATG – Medical target system design support
Nuclear Physics Department – FLUKA support, CANREB support, MPS, operations manuals, TIS development
C

## Slide 15: Open Work Packages
There are several design and installation packages that ARIEL is looking for support with.
  Pre-separator integration (support stand)
  ALIS integration (connecting the laser ion source system to the ARIEL pre-separator)
Assembly of Wire Scanners and BPMs could be performed by other TRIUMF technicians to take load off of diagnostics group. Would require training.
UHV cleaning of beampipes & vacuum envelope components
Mapping Magnet Stray fields of optics

## Slide 16: Development Contributions
The TISA target and ion source test stand will be used to test target ion source front ends before installation in late 2025. After that the system is available for target and ion source development. Stefan Malbrunot is interested but needs support.
  Developing mass markers
  Long-term testing and calibration of AETE/APTW target geometry
  Thick target container wall
  Integrate the FEBIAD into ARIEL HTV, including calibrated leak, gas delivery
  IG-LIS, including RF delivery
  CTL, variable transfer line

## Slide 17: Individual Contributions
In 2025:
  Design and fabrication support (targets, target modules, RIB diagnostics, removable shielding components, waste drum handling tools…)
  Procurement support
  Support in defining controls and interlock documentation
  Electronics development
  Collecting commissioning inputs and support/coordinate/write commissioning documentation
  Collecting licensing inputs and support/coordinate/write commissioning documentation
  Operations manuals
  Module assembly and assembly coordiation
For the installation in 2026:
  Installation technical support
  Cable management and cable pulling
  Coordinate or support subsystem testing
  Support in moving ISAC target laboratories and setting up ARIEL target laboratories

## Slide 18
Discovery,
accelerated
Thank you Merci
Follow us @TRIUMFLab
www.triumf.ca

## Slide 19: BACKUP

## Slide 20: Milestone Trend Analysis
C
Chart: P342 - Program Milestone Trend Analysis
Previous Period | 1
LS 2026 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46204 | 46205 | 46204 | 46204
CFI: Photo-fission Rare Isotope Beam to yield station - 4584 | 45912 | 45904 | 45904 | 45911 | 45904 | 45909 | 45912 | 45912 | 45912 | 45912 | 45912 | 46083 | 46057 | 46057 | 46052 | 46101 | 46100 | 46161 | 46148 | 46154 | 46140 | 46140 | 46160 | 46170 | 46192 | 46227 | 46335 | 46364 | 46388 | 46367 | 46457 | 46472 | 46500 | 46519 | 46533 | 46533 | 46665 | 46665 | 46703 | 46702 | 46702 | 46703 | 46675 | 46700 | 46784 | 46770 | 46814 | 46779
APTW Gate 4A Review - Readiness for Commissioning / CFI: RIB from ARIEL Proton Target West to yield station - 11006 | 46100 | 46100 | 46100 | 46100 | 46100 | 46100 | 46100 | 46100 | 46100 | 46233 | 46233 | 46391 | 46366 | 46366 | 46363 | 46409 | 46408 | 46430 | 46419 | 46423 | 46409 | 46409 | 46409 | 46441 | 46463 | 46498 | 46604 | 46633 | 46470 | 46449 | 46612 | 46629 | 46657 | 46674 | 46688 | 46688 | 46820 | 46820 | 46860 | 46857 | 46857 | 46766 | 46647 | 46628 | 46591 | 46533 | 46533 | 46561
Therapeutic Isotopes Gate 4A Review - Readiness for Commissioning - 14074 | 46448 | 46303 | 46255 | 46303 | 46303 | 46303 | 46303 | 46303 | 46330 | 46436 | 46465 | 46470 | 46504 | 46539 | 46554 | 46582 | 46601 | 46615 | 46615 | 46745 | 46745 | 46785 | 46784 | 46784 | 46785 | 46787 | 46799 | 46731 | 46673 | 46673 | 46701
AETE Gate 4A Review - Readiness for Commissioning / CFI Ions from AETE to ISAC - 5915 | 45702 | 45694 | 45694 | 45702 | 45694 | 45699 | 45702 | 45702 | 45702 | 45702 | 45702 | 45867 | 45842 | 45842 | 45838 | 45888 | 45887 | 45897 | 45936 | 45953 | 45926 | 45926 | 45947 | 45959 | 45982 | 46027 | 46134 | 46163 | 46189 | 46168 | 46258 | 46273 | 46301 | 46318 | 46332 | 46332 | 46464 | 46464 | 46504 | 46503 | 46503 | 46504 | 46476 | 46499 | 46583 | 46569 | 46615 | 46580
Start Installation of Target Modules, RIB Modules and Infrastructure - 10303 | 45362 | 45352 | 45352 | 45359 | 45352 | 45357 | 45362 | 45362 | 45362 | 45362 | 45369 | 45366 | 45343 | 45343 | 45337 | 45390 | 45387 | 45400 | 45399 | 45369 | 45418 | 45418 | 45420 | 45418 | 45418 | 45475 | 45475 | 45532 | 45576 | 45586 | 45687 | 45702 | 45733 | 45750 | 45764 | 45764 | 45853 | 45853 | 45862 | 45884 | 45884 | 45884 | 45884 | 45884 | 45992 | 45931 | 45931 | 45931
AETE T/IS FE Detailed Design Complete - 13991 | 44778 | 44802 | 44802 | 44834 | 44834
Gate 3 Review AETE HVFT - 10542 | 44606 | 44592 | 44592 | 44592 | 44628 | 44687 | 44687 | 44693 | 44693 | 44698 | 44718 | 44727 | 44735 | 44760 | 44781 | 44826 | 44826 | 44901 | 44965 | 44952 | 44979 | 44979 | 44998 | 45041 | 45063
Target Pit Shielding Construction Re-started (after Hot Cell) - 13882 | 44803 | 44802 | 44813 | 44813 | 44851 | 44789
Current Date Line | 44316 | 44347 | 44377 | 44408 | 44439 | 44469 | 44500 | 44530 | 44561 | 44592 | 44620 | 44651 | 44681 | 44712 | 44742 | 44773 | 44804 | 44834 | 44865 | 44895 | 44926 | 44957 | 44985 | 45016 | 45046 | 45077 | 45107 | 45138 | 45169 | 45199 | 45230 | 45260 | 45291 | 45322 | 45351 | 45382 | 45412 | 45443 | 45473 | 45504 | 45535 | 45565 | 45596 | 45626 | 45657 | 45688 | 45716 | 45747 | 45777 | 45808
The sequencing of AETE and APTW installation in a result of resource leveling, not technical limitation.