## Slide 1: UBC/TRIUMF February 2026 General Meeting

## Slide 2
UBC System Status, Plan, & Milestones
UBC Agenda:
Testing History: Colin [5 mins]
Laser status and plan: Taka/Colin [20 mins]
H source and benders status and plan: Taka/Colin [20 mins]
Decelerator commissioning status and plan: Giulia/Tony/Taka/Colin [25 mins]

## Slide 3
Testing Timeline – Last Few Months
November 7th: Started installing THG cell, vacuum line, and laser system at decelerator testing station.
December 1st: Setup of longer decelerator section with all sub-systems complete.
December 1st-12th: Spent 2 weeks doing free flight measurements and guiding with no success.
December 15: Setup smaller decelerator section for higher chance of seeing signal (1 week setup time).
December 22: First tests and free flight detected on December 23rd.
January 5th-19th : Testing resumed with intermittently with some delays due to leaks and laser power.
January 19th-Feb 4th : Nozzle leaking issues.
February 5th: First tests since January 19th.

## Slide 4
Laser Status and Plan – 10 Hz (UBC)
Status:
10 Hz laser fully commissioned and functional at both source testing area as well as the decelerator testing area. Redirect one mirror to change laser path.
  Source Testing Area:
    365 nm: 16 mJ
    121 nm: 60 mV / 2.2 nJ
  Decelerator Testing Area:
    365 nm: 12 mJ
    121 nm: 15 mV / 0.5 nJ

## Slide 5
Laser Status and Plan – 10 Hz (UBC)
Challenges:
Opto-mechanical drift over time from thermal cycling, heat change, and vibrations.
  Re-alignment solves this
Optics degradation over time from handling, humidity, and dust.
  Mirrors and windows being cleaned solve this
Power stability from diode aging and drift
  Replacing diodes and checking alignment fixes this
Locking reference issues from temperature changes in laser area
  Fixing HVAC system solves this

## Slide 6
Laser Status and Plan – 50 Hz (TRIUMF)
Status:
All components are ordered and on hand.
System to be assembled and tested before it is brought to TRIUMF.
Plan:
Taka and Sahara will setup and commission 50 Hz system in the next few months.
System will be built on breadboards so that it can be easily moved to TRIUMF.
Obtain stable 365 nm  obtain stable 121 nm  move to TRIUMF once laser area is ready at TRIUMF.

## Slide 7
Hydrogen Source Status and Plan
Status:
2 different source chambers are assembled and in use.
  1 is at source testing area (larger chamber)
  1 is at decelerator testing area.
  Having both setups allows for testing of different configurations during downtime at other source chamber which is beneficial.
Both setups are using CRUCS valves with pinhole discharge, which have been shown to be the most effective setup in terms of density and repeatability.
Testing different quartz tubes (ID, OD, coatings), and pinhole discharge configurations.
This is being done in parallel to our free flight / guiding / deceleration testing.

## Slide 8
Hydrogen Source Status and Plan
Plan:
Using CRUCS valves with pinhole discharge moving forward.
Coat quartz and SS tubing in Teflon coating to see if this fixes signal degradation.
  1st we will test a Teflon liner inside both tubes (ordered from Zeus Inc.)
  If this doesn’t work we try PTFE electroless coating (Coating Tech. Inc.)
Manufacturing a pinhole discharge with ceramic only (vs ceramic/polymer composite) insulating layers to test if this fixes arcing / inconsistent discharge.

## Slide 9
Halbach and EM Bender Status and Plan
Status:
Halbach bender parts have all been received and inspected for accuracy.
EM bender design is complete and ready to be manufactured.
Some questions surrounding simulation results of EM bender.
Plan:
Halbach bender to be assembled and tested at source testing area.
Goal is to determine change in signal between free flight / guiding through bender.
EM bender to be manufactured by UBC Mech Shop.

## Slide 10
Decelerator Status
The decelerator can create guiding and deceleration waveforms for the range of velocities that the source appears to create.
The decelerator can be controlled with both LabView and python.
There has been detection of free flight hydrogen signal but no guided signal.
Currently conducting free flight and guiding scans to achieve consistent results.
Development of Python control integration with MIDAS is currently not a priority, but remains a task.

## Slide 11
Free Flight Scan Results

## Slide 12
Free Flight Scan Results

## Slide 13
Free Flight Scan Results

## Slide 14
Free Flight Scan Results

## Slide 15
Free Flight Scan Results – Source Testing Area vs Decelerator Testing Area

## Slide 16
Decelerator Plan
Implement changes to increase SNR and continue free flight and guiding scans.
If a guiding signal is detected → conduct deceleration scans.
Test Halbach bender between source and decelerator.
Test EM bender after decelerator.

## Slide 17: Click to edit Master title style