## Slide 1: P353 Overview ARIEL Target Stations ASSC Fall 2026
Oct 1-2, 2026
Project Leader:
Trian Groumoutis
Project Integrator:
Luca Egoriti

## Slide 2: P353 Scope
AETE
Vacuum System & Radioactive Gas Storage
APTW
ALIS
HV Terminal & Electrical services
Auxiliary Gas services (N2, Ar)
Medical module
HV Service Chase
HV Service Chase
Secondary Gas Recirculating and Delay systems
High Active Water and Active Low Conductivity Water systems
Proton beam
Electron beam
RIB
RIB

## Slide 3: P353 Scope
Structural Supports
Gamma Dump Module
Target Access Plug
Target Module
Converter Module
HVFT
HTV
AETE
TIS FE

## Slide 4: P353 Scope
APTW
Target Module
Medical Module
Beam Dump
Target Access Plug
HVFT

## Slide 5: Accomplishments Since Last ASSC Meeting
HTVs and Targets
  APTW parts procured, one HTV previously completed
  AETE low power HTV designs completed and parts procured, awaiting finish machining
  AETE low power targets in progress

## Slide 6: Accomplishments Since Last ASSC Meeting
Target Modules
  First Target Module (TM1 for APTW) completed and ready for integrated testing
  Second Target Module (TM2 for AETE) FE and Shield plug assembled
    Small pieces to assemble before integration
    Waiting for TM1 to vacate assembly frame

## Slide 7: Accomplishments Since Last ASSC Meeting
HVFT
  HVFT-TM1 procurement
    Both potting operations completed
    Epoxy ends need slight repair and re-potting, in progress
  HVFT-TM2 procurement
    Vendor received all parts from TRIUMF
    Assembly of prepared services in HV core starting
  HVFT Clamshell Shielding
    All three sets of clamshell components arrived
    Once clamshell assembled and inserted into TM1 with dummy HVFT plug
  HVFT clamshell assembly/maintenance flange
    Received and waiting for assembly

## Slide 8: Accomplishments Since Last ASSC Meeting
Target Access Plugs
  Fully assembled and waiting for transport to target
Converter Module
  Shield plug and cold plate assembled
  In storage frame waiting for FE (in progress in machine shop)

## Slide 9: Accomplishments Since Last ASSC Meeting
APTW Beam Dump
  Assembled shield plug and welded water lines
  Assembled core
  Module fully assembled and pressure tested
  Waiting for transport to target hall

## Slide 10: Accomplishments Since Last ASSC Meeting
Medical Module
  Shield plug assembled
  Phase 2 and 3 testing completed (mechanical and water)
  Final development and procurement/manufacturing and Phase 4a testing in progress

## Slide 11: Accomplishments Since Last ASSC Meeting
Support Structures
  Cooling panels installed
  Shielding blocks and assemblies installed
  Copper gap cover installed
  Drip trays – one received, one being fabricated

## Slide 12: Accomplishments Since Last ASSC Meeting
High Voltage Chases
  APTW installed (target hall and B1-08) and tested to 75 kV
  AETE 60% complete - most difficult part done, further content in B1-08 and target hall in progress

## Slide 13: Accomplishments Since Last ASSC Meeting
High Voltage Terminal
  Isolation transformer stand built and placed
  AETE and APTW enclosures in progress

## Slide 14: Accomplishments Since Last ASSC Meeting
Top Service Tray
  Substantial design development – partially released
  Procurement of off-the-shelf parts
  WO’s pending in the machine shop

## Slide 15: Accomplishments Since Last ASSC Meeting
Nitrogen and Argon distribution
  Cryogenic portion for N2 completed
  Supply banks for Argon procured and placed
  TPSR scope completed for both
  Procurement, installation, and commissioning following regulatory compliance

## Slide 16: Accomplishments Since Last ASSC Meeting
Secondary Gas Recirculation and Delay Line
  Secondary gas box arrived
  Filter stands assembled and placed, ready for installation
  Substantial installation of delay line in ARIEL tunnel and proton cave
  Large volume tanks in lower level for delay previously installed, tubing interconnections between tanks and connection to system in progress

## Slide 17: Accomplishments Since Last ASSC Meeting
Radioactive Gas Storage and Vacuum
  Radioactive gas storage tank arrived tested and installed
  Interconnect tubing installed, shielding placed, and tanks grouted
  Distribution manifold assembled, tested, and installed
  AETE roughing and backing line weldments installed

## Slide 18: Accomplishments Since Last ASSC Meeting
High Active Water & Active Low Conductivity Water
  Two contracts underway
  Substantial completion of both target hall and TPSR scope

## Slide 19: Accomplishments Since Last ASSC Meeting
Electrical
  Massive number of cables - many purchased, cut, and ready to pull
  Installation of cable trays, EMTs
  Designs and procurement for grounding, power
Controls
  Development of control narratives and interlocks for all systems
  Procurement of PLCs and other key components ongoing
  Development for TISA and Secondary Gas system

## Slide 20: Accomplishments Since Last ASSC Meeting
TISA
  Installation of third FE from SCK-CEN
  Extension of TISA beam line with magnet

## Slide 21: Progress on Plans Presented at previous ASSC Meeting
“ “ = priority changed
Further slippage could affect the critical path
Task is ongoing and further slippage won’t affect the critical path
On track or finished
Next two slides cover previous task status
Colour coded based on impact

## Slide 22: Progress on Plans Presented at previous ASSC Meeting
Priority | Objective | Task Owner | Scheduled Date | WBS Comments/Status | Big picture reference
1 | TM1 assembled | LE | MAY 26 | Assembly complete Final measurements and prep for integrated test underway | Ready for integrated testing with other modules before moving into the target hall
3 | Uninstall FE#2 from TISA and install SCK FE (FE#3) | LE |  | Front Ends successfully swapped | TISA needed for target testing and prepare/train team for commissioning
1 | HVFT #1 arrived on site | AL | JAN 25 | Second resin curing complete, third WIP for touch-up Preparation and leak checking for second VPI took excessively long Engineer sent to aid with leak checking and VPI, greatly sped up process | Needed for offline (fitting) tests in ISAC-I assembly frames If not ready for testing in ISAC-I, backup plan for TH
1 | HVFT #2 HV core potting completed | AL | MAY 26 | Core potting not completed yet All parts and materials on-hand for assembly HVFT 1 prioritized | Needed for offline (fitting) tests in ISAC-I assembly frames If not ready for testing in ISAC-I, backup plan for TH
1 | All CM parts including FE ordered and manufactured | TG | MAY 26 | Shield plug assembled Front end deprioritized, in progress in machine shop | Transported to target hall in later batch
2 | Secondary gas box assembled and ready for testing | SciTech | MAY 26 | Gas box weldment fabricated and delivered All other components procured Assembly and/or install starting | Sequence in services room requires careful coordination with other service installations
1 | Radioactive gas storage tanks installation below false floor | SciTech | MAR 26 | Tanks, shielding, tubing, grout, and manifold all installed and tested | First item in the install sequence of vacuum space Enabled installations of HV chase, HAW, false floor
1 | APTW HV chase: installed | TPO | APR 25 | Both target hall and B1-08 sides installed Target hall section tested to 75 kV Remaining work is final connections to adjacent systems and window covers following cleaning | Second major installation after target hall fixed shielding construction finished
2 | AETE HV chase: installed | TPO | JUN 26 | Substantial installation in B1-08 and vacuum package space Most difficult portion completed | At the moment, other systems are critical path for P353

## Slide 23: Progress on Plans Presented at previous ASSC Meeting
Priority | Objective | Task Owner | Scheduled Date | WBS Comments/Status | Big picture reference
2 | HV terminal installation started | TPO | APR 26 | Installation started and making progress | Needed for full HV infrastructure testing
2 | Nitrogen distribution install start | SciTech | APR 26 | TPSR and Cryogenic potions installed Preparations underway for further installations in ISAC-I | Equipment interfaces and supplies several other systems: HAW, pillow seals, pistons, sec gas. Needed for station commisioning
1 | AETE HTV ready for testing | NN | JUN 26 | All external manufactured and procured parts received Custom PEEK seal order being worked out Final machining in queue in machine shop | Needed for integrated module testing Long delay may result in delay in module transport to target hall
2 | Controls narrative for target stations developed | AS | JUN 26 | Controls narratives developed and either released on in final review | Key input for interlocks and controls team Support functional testing prior to commissioning
2 | HAW installation in TPSR started | AW | JUN 26 | Contractors have started and to date have installed a lot of content | Part of integrated TPSR installation plan
1 | Medical module integrated testing finished | LE | JUN 26 | Phase 4a testing and manufacturing in progress, moving towards full module integration | Module still on track for completion in LS26

## Slide 24: MTA Update
Chart: P353 - Program Milestone Trend Analysis - ALL
Previous Period
AETE Target Station services ready for connection to modules - 14057 | 45763 | 45778 | 45826 | 45826 | 45826 | 45826 | 45826 | 45826 | 45859 | 45968 | 45909 | 45933 | 45912 | 46006 | 46029 | 46057 | 46077 | 46091 | 46091 | 46223 | 46223 | 46261 | 46260 | 46260 | 46261 | 46233 | 46258 | 46342 | 46328 | 46372 | 46337 | 46414 | 46423 | 46423 | 46470 | 46470 | 46470 | 46464 | 46486 | 46486 | 46486 | 46486 | 46486 | 46449 | 46449 | 46512 | 46500 | 46514
APTW Target Station services ready for connection to modules - 14073 | 46175 | 46162 | 46168 | 46154 | 46154 | 46174 | 46184 | 46206 | 46241 | 46349 | 46350 | 46374 | 46353 | 46443 | 46458 | 46486 | 46505 | 46519 | 46519 | 46651 | 46651 | 46689 | 46688 | 46688 | 46261 | 46233 | 46258 | 46342 | 46328 | 46372 | 46303 | 46272 | 46391 | 46391 | 46440 | 46440 | 46409 | 46402 | 46444 | 46444 | 46423 | 46423 | 46428 | 46449 | 46449 | 46486 | 46500 | 46514
Medical Module Design review - COMPLETE - 14630 | 45793 | 45804 | 45831 | 45831 | 45831 | 45831 | 45856 | 45856 | 45856 | 45856 | 45856 | 45856 | 46139 | 46101 | 46101 | 46101 | 46101 | 46101 | 46129 | 46150 | 46150 | 46150 | 46150 | 46150 | 46150 | 46290 | 46290 | 46290 | 46325 | 46325 | 46325 | 46325
Medical Module ready to transfer into hot cell - COMPLETE - 14632 | 45833 | 45861 | 45861 | 45861 | 45861 | 45888 | 45888 | 46189 | 46189 | 46189 | 46189 | 46265 | 46265 | 46265 | 46265 | 46373 | 46373 | 46373 | 46373 | 46373 | 46373 | 46384 | 46402 | 46402 | 46360 | 46346 | 46346 | 46381 | 46381 | 46381 | 46381
Medical Module ready for commissioning - 15184 | 46316 | 46461 | 46448 | 46349 | 46349 | 46349 | 46423 | 46457 | 46457 | 46457 | 46457 | 46457 | 46457 | 46468 | 46486 | 46486 | 46444 | 46430 | 46430 | 46465 | 46465 | 46465 | 46465
Medical module ready by end of LS26
Target station modules and services complete by end of LS26
Target stations preparing for commissioning

## Slide 25: Major Risks, Issues, Concerns
Risk/Issue | Comments and Mitigations
HVFT arrival delay | Schedule risk, mitigated by its assembly in the ARIEL TH and not in assembly area. Also sending TRIUMF engineer to vendor to speed things up
Resources availability from groups assigned to “P353 packages” | Tight coordination with PMO to make sure resources from other groups with resource availability can contribute/support P353 when needed
Space limitations in module assembly area, preventing assembly of equipment (modules) ready to be assembled | Active assembly coordination team Scheduling equipment in a way compatible with module moves into the ARIEL target hall Separate sub-assemblies in progress elsewhere
Unforeseen work - Cleaning, preparation, shared areas | Schedule risk, tasks taking longer than foreseen since lots of unforeseen prep work not planned for. Effort to prep early and thoroughly and reacting fast to field conditions, active coordination
Manufacturing timelines have slipped for noncritical items which will become critical soon | Very tight coordination with manufacturing department head, and prioritization of machining sequence within each work order submitted, part by part, where timeline is critical for installation

## Slide 26: LS 26

## Slide 27: Gate 3 Readiness
Task​ | Status (Yes/No/%)​ | Comment​
All released documents up-to-date?​ | 90%​ | Remaining: one RS, interlocks, Eng Notes
Commissioning plan drafted?​ Note: Different types of projects have different criteria and terminology for ‘commissioning’ ​ | Yes | ARIEL commissioning plan, in progress
Drawings, diagrams or schematics released by ECO?​ | 100% (modules)​ 90% (Services)​ | Components requiring field measurements and connection details
All Requirements Specification documents released to Docushare?​ | 95%​ | HAW (Rev 2) remaining
Schedule critical path understood?​ | Yes​ | HVFT, Services in service spaces
Budget by fiscal year is updated and remaining funds enough to cover projected costs?​ | Yes | Adequate funds to complete project
Have you sent to the Procurement Department a list of all major items (>$75k) to be purchased, with a timeframe, and agree with them on a procurement strategy for each? ​ Note: List major in next 6 months​ | Yes | No major items > 75kCAD remaining
Top risks identified, with credible mitigation actions?​ | Yes​ | See previous slide​
Integration and test plans reviewed by experts and project stakeholders (e.g. users)?​ | 20%​ | Incomplete drafts getting close to review
Controls (EPICS, data acquisition, MPS, etc.…) specified?​ | 40%​ | Controls narratives reviewed​ or released. Interlocks WIP or reviewed or released
Summary of lessons to learn thus far, presented at Gate review?​ | No ​ | only technical and not formally recorded

## Slide 28: Plans and Objectives for the Next 6 Months
Priority | Objective | Task Owner | Scheduled Date | WBS Comments/Status | Big picture reference
1 | HVFT #1 delivered | AL | NOV 26 | Second resin curing complete, third WIP for touch-up Preparation and leak checking for second VPI took excessively long | Needed for offline (fitting) tests and integration in ISAC-I assembly frames If not ready for testing in ISAC-I, backup plan for TH
1 | HVFT #2 delivered | AL | FEB 27 | Core potting not completed yet All parts and materials on-hand for assembly HVFT 1 prioritized | Needed for offline (fitting) tests and integration in ISAC-I assembly frames If not ready for testing in ISAC-I, backup plan for TH
1 | APTW TM integrated testing complete | MG | NOV 26 | Functional and vacuum tests complete at ISAC-I testing and assembly frames | Module ready for move to target hall
1 | AETE HV chase: installed | TPO | NOV 26 | Completion of remaining target hall and vacuum package content | Enables further installation in vacuum package Key system for integrated testing
2 | Secondary Gas Handling Unit installed | SciTech | DEC 26 | Welded assembly received, sub-assemblies ready, procured parts in-hand Installation and assembly go hand-in-hand | Installed at opportune time for TPSR access Key system for integrated testing
1 | Nitrogen distribution installed | SciTech | MAY 27 | Design documents completed Routes planned, detailed implementation in progress Purchasing, regulatory requirements, all under way | Last major infrastructure completed Enables station integrated testing
1 | Radioactive gas pit install complete | FR | MAR 27 | Installation below false floor complete Design, manufacturing, and procurement of above false floor content in progress | Enables further station vacuum installation leading to station integrated testing Vacuum systems also on critical path
1 | Medical module integrated testing finished | LE | JAN 27 | Phase 4a testing and manufacturing in progress, moving towards full module integration | Integrated module ready for move to target hall

## Slide 29
Discovery,
accelerated
Thank you Merci
Follow us @TRIUMFLab
www.triumf.ca