## Slide 1: P354 Overview ARIEL Pre-Separator and RIB Transport ASSC Fall 2026
Oct 1-2, 2026
Project Leader:
Marco Marchetto
Project Integrator:
Dave Wager

## Slide 2
P354 Project Scope Overview, Outside ARIEL Target Hall

## Slide 3
P354 Project Scope Overview, ARIEL Target Hall

## Slide 4: Recent Accomplishments – RIB Module Assembly

## Slide 5: Recent Accomplishments – RIB Module Assembly

## Slide 6: Recent Accomplishments – RIB Module Assembly

## Slide 7: Recent Accomplishments – Module Mounting System Installation

## Slide 8: Recent Accomplishments – Module Mounting System Installation

## Slide 9: Recent Accomplishments – Manufacturing & Installation

## Slide 10: Progress on Plans Presented at previous ASSC Meeting
From the previous ASSC:
  RIB Modules 1-4 assembly complete, including HV tests and vacuum leak check
  RIB Module 5 & 6 procurement complete and approaching assembly readiness
  APTW Entrance Module design released and purchase order issued
  APTW Module Mounting System installation nearing completion
  AETE & APTW Pre-Separator magnet subassemblies complete
  AETE Raster magnet subassembly complete
Module assembly, alignment and leak checking is complete. Combined vacuum testing and various functional checks remain.
Module shielding order was submitted in May and is nearing completion at the vendor. Vacuum doglegs and RIB 5 vacuum chambers are complete. Plans for filling the shielding blocks are in ongoing development.
All designs released and orders submitted. Shielding has been received. In house machining and fabrication for subassemblies is nearly complete, and last vendor parts are expected in September.
Module Mounting System installation is complete for both stations.
Pre-separator supports have been installed in both target pit locations. Target hall installation has been scheduled for November, with final magnet preparation underway.
One raster core assembly is complete and ready for testing. The second core is in final assembly and will be available for combined testing (and further controls development) by end of September.

## Slide 11: MTA Update

## Slide 12: Major Risks, Issues, Concerns
Risk | Mitigation
Issue: Shipment of a 2nd set of rad-hard cables for entrance module diagnostics was delayed (vendor error). | Cables initially intended for AETE entrance module assembly will be used for APTW, AETE final assembly may be pushed out.
Risk: RIB Module 6 assembly is unique. Both vacuum box and shielding assembly may take longer than anticipated. | Prioritize & align assembly activities to limit impacts of possible delays.
Risk: Delayed subcomponents could lead to overlapping assembly timelines between APTW Entrance Module, RIB Modules 5 & 6 (low probability) | Few options available to accelerate one package over others. Prioritize pre-planning activities to limit downtime.

## Slide 13: LS 26

## Slide 14: Gate 3 Readiness
Task​ | Status (Yes/No/%)​ | Comment​
All released documents up-to-date?​ | 95% | See below re: test plans
Commissioning plan drafted?​ Note: Different types of projects have different criteria and terminology for ‘commissioning’ ​ | Yes | Functional test plan draft exists, currently in revision. Beam-level commissioning plan drafted.
Drawings, diagrams or schematics released by ECO?​ | 95% | Only top-level assemblies or small miscellaneous components and revisions
All Requirements Specification documents released to Docushare?​ | Yes | 
Schedule critical path understood?​ | Yes | 
Budget by fiscal year is updated and remaining funds enough to cover projected costs?​ | No | Overall project budget exceeded by ~3%, with less than $25k total spend remaining
Have you sent to the Procurement Department a list of all major items (>$75k) to be purchased, with a timeframe, and agree with them on a procurement strategy for each? | N/A | No remaining procurement packages of this size
Top risks identified, with credible mitigation actions?​ | Yes | 
Integration and test plans reviewed by experts and project stakeholders (e.g. users)?​ | Partial | See above
Controls (EPICS, data acquisition, MPS, etc…) specified?​ | Yes | Control of new devices has been tested / demonstrated
Summary of lessons to learn thus far, presented at Gate review?​ | Yes | 

## Slide 15: Plans and Objectives for the Next 6 Months
RIB Module assembly complete in ISAC I
Combined testing of APTW modules complete in ISAC I
First module move to target hall complete
Pre-separator magnet installation complete
AETE Raster assembly complete, progress on testing and controls development

## Slide 16
Discovery,
accelerated
Thank you Merci
Follow us @TRIUMFLab
www.triumf.ca